## Agile User Story Template
AGILE USER STORY TEMPLATE
USER STORY ID | As a <type of user> | I want to be able to | so that I can <achieve some goal> | Priority | Status [time being]
1 | User | Register | create an account | 1 | Done
2 | User | login using credentials | get flight details and book ticket with id | 1 | Done
3 | User | View booking | Able view my booking details | 2 | Work in Progress
4 | User | Search | able to search the flights | 1 | Work in Progress
5 | User | edit personal info | Update my personsal details | 1 | Done
6 | User | Reset Password | abe to get link to rest password | 2 | Work in Progress
7 | User | book flight | know bookingId , flightDetails , passengerDetails,ticketid | 1 | Work in Progress
8 | User | view ticket | able to know departureTime,airportName | 1 | Work in Progress
9 | User | logout | able logout from the website | 1 | Work in Progress
CLICK HERE TO CREATE IN SMARTSHEET

## Task-Assigned-Sheet
Sl.No | Task name | Assigned To | Started Date | Completed On
1 | User Story | Nandini & Priya | 18/08/2020 | 18/08/2020
2 | Backend Login & Register | Manohar | 18/08/2020 | 20/08/2020
3 | Flight Dummy DB | Mohan | 18/08/2020 | 19/08/2020
4 | Search Flight backend | Attimabbe | 18/08/2020 | 19/08/2020
5 | View Bookings | Nandini & Attimmabe | 19/08/2020 | 20/08/2020
6 | Edit User | Priya | 19/08/2020 | 20/08/2020
7 | Reset Password | Manohar | 19/08/2020 | Work in Progress
8 | Login and Register | Attimabbe